## Tabular View
UPDATED WORK BREAKDOWN STRUCTURE (WBS)
PROJECT TITLE |  | PES 2019 - PROJECT II
PROJECT NUMBER |  | PROJECT 2
PROJECT MANAGER |  | ATHARV DESAI, SURAJ THITE
CLIENT/SPONSOR |  | BRUCE MONTGOMERY
DOCUMENT DATE |  | 2019-10-03 |  |  |  |  | Tabular View
UPDATED TABLE SIGNS
Sr No. | INDICATIONS | MEANING | 1 | WORK BREAKDOWN STRUCTURE | 2 | CODE AND MAKE FILES | 3 | EXTRA CREDITS | 4 | FINAL SUBMISSION
1 | -Goal Met | Goal achieved | 1.1 | TENTATIVE WBS - Atharv (M) (Goal Met) | 2.1 | fb_run: (Goal Met) | 3.1 | CAPACITIVE SLIDER (Not Met) | 4.1 | ESE C STYLE GUIDE (Goal Met)
2 | - Goal Not Met | Goal not achieved due to time constraints | 1.1.1 | Project Goals - Suraj (M) - Goal Met | 2.1.1 | Sequential Flashing of LEDs - Atharv (M) - Atharv (S) | 3.1.1 | Slider Area Divison. - Atharv (M) - Goal Not Met | 4.1.1 | Function Description. - Atharv (M) --> Suraj (M)
3 | Person A --> Person B/A | Owner swap or timing change | 1.1.2 | Task Analysis - Suraj (M) - Goal Met | 2.1.2 | Time Delay Loop - Atharv (M) - Atharv (L) - Goal Met | 3.1.2 | Color allocation w.r.t slider area - Suraj (M) - Goal Not Met | 4.1.2 | File Information. - Atharv (S) - Goal Met
|  |  | 1.1.3 | Task Allocation- Atharv (M) - Goal Met | 2.1.3 | LED Color Change - Suraj (M) - Goal Met | - | - | 4.1.3 | Compilation and Error checks- Suraj (M) --> Suraj (L)
|  |  | 1.1.4 | Project Timeline - Suraj (S) - Goal Met | 2.1.4 | Make File - Suraj (L) - Goal Met | - | - | 4.1.4 | Commenting - Suraj (M) - Goal Met
|  |  | 1.2 | UPDATED AND FINAL WBS(Goal Met) | 2.2 | fb_debug:(Goal Met) | 3.2 | Real Time Clock (Goal Met) | 4.2 | PDF DOCUMENTATION (Goal Met)
|  |  | 1.2.1 | Comparison with TENTATIVE WBS - Atharv (M) --> Suraj (S) | 2.2.1 | fb_run inheritance - Suraj (L) - Goal Met | 3.2.1 | Initialization - Atharv (M) --> Suraj (S) --> Atharv (M) | 4.2.1 | README- Suraj (M) - Goal Met
|  |  | 1.2.2 | Updation w.r.t time constraints- Suraj (M) --> Suraj (S) | 2.2.2 | UART Config - Suraj (M) --> Atharv (M) | 3.2.2 | Time Stamping- Suraj (M) --> Atharv (M) --> Suraj (L) | 4.2.2 | WBS - Atharv (S) --> Suraj (S)
|  |  | 1.2.3 | Final improvisation of WBS - Atharv (M) - Goal Met | 2.2.3 | Time Stamping - Atharv (M) - Goal Met | - | - | 4.2.3 | C CODE - Atharv (S) - Goal Met
|  |  | - | - | 2.2.4 | START & END Messages - Atharv (M) - Atharv (L) | - | - | 4.2.4 | MAKE FILE TEXT Suraj(S) --> Atharv (S)
|  |  | - | - | 2.2.5 | Updation of Make File - Suraj (M) - Goal Met | - | - | 4.3 | README FILE (Goal Met)
|  |  | - | - | 2.3 | pc_run:(Goal Met) | - | - | 4.3.1 | Description of of Repo Contents. - Suraj (S) - Goal Met
|  |  | - | - | 2.3.1 | Inheritance of fb_run. - Suraj (M) - Goal Met | - | - | 4.3.2 | Installations/Execution Notes. - Atharv (S) - Goal Met
|  |  | - | - | 2.3.2 | LED Status via text - Atharv (M) - Goal Met | - | - | 4.3.3 | Documents Integrity. - Suraj (S) - Goal Met
|  |  | - | - | 2.3.3 | Synchronization of timing loops - Suraj (M) - Suraj (L) | - | - | 4.3.4 | Final Commit. - Atharv (M) --> Suraj(S)
|  |  | - | - | 2.3.4 | Updation of Make File - Atharv (L) - Goal Met | - | - | - | -
|  |  | - | - | 2.4 | pc_debug:(Goal Met) | - | - | - | -
|  |  | - | - | 2.4.1 | Inheritance of pc_run - Atharv (M) - Atharv (L) | - | - | - | -
|  |  | - | - | 2.4.2 | Time Stamping - Atharv (L) - - Goal Met | - | - | - | -
|  |  | - | - | 2.4.3 | Status on debug console - Suraj (M) - Goal Met | - | - | - | -
|  |  | - | - | 2.4.4 | Make File - Suraj (L) - Goal Met | - | - | - | -
-